## Slide 1: Ashville Pork: Continuous Improvement Project
Presented by: Shoaib Malik
Date: 29-07-2025

## Slide 2: Project Overview
Objective: Improve operational efficiency and workforce engagement via Continuous Improvement (CI)
Scope: Staff training, pilot projects, cross-site collaboration
Outcome: Sustainable CI culture across both sites

## Slide 3: Stakeholder Involvement
Key Stakeholders:
- MD, HR Director, Operations Director, Finance Director
- Site Managers (North & South), Employees, Commercial Director, Supermarket Client
Roles: Assigned via RACI Matrix
Engagement: Weekly to monthly interactions based on influence/importance

## Slide 4: Influence / Importance Matrix
B – High Influence, High Importance: MD, HR Director, Site Managers
A – High Importance, Low Influence: Employees
D – Low Importance, High Influence: Commercial Director
C – Low Influence, Low Importance: Supermarket Client

## Slide 5: Key Activities / Priorities
1. CI Training Rollout
2. Site Engagement and Pilot Launch
3. Cross-site Resource Sharing
4. Feedback Collection and Iteration
5. Senior Leader Check-ins
6. Financial Tracking
7. Stakeholder Updates
8. Final CI Adoption

## Slide 6: Meeting Stakeholder Needs
Equal participation across both regions
Clear communication and transparency
Strong financial oversight
Quality assurance during changes
Inclusion of all staff levels

## Slide 7: Timeframes & Milestones
Month 1: Stakeholder alignment & communication
Month 2–3: Training & pilot testing
Month 4: Review & adjust
Month 5: Expansion across sites
Month 6: Project evaluation

## Slide 8: Conflicts & Mitigations
Resistance from board: Engage early, share data
Site imbalance: Rotate benefits, equal say
Training time conflicts: Adjust schedules
Cost concerns: Staged investment, prove ROI

## Slide 9: What Success Looks Like
90%+ staff trained in CI tools
At least 3 measurable process improvements
Increased employee ownership & feedback
Waste reduction & higher productivity
Retained client confidence

## Slide 10
Thank you
Open to feedback and suggestions
Contact info: Shoaib Malik
dtc0823013@nttf.co.in